## Project Log
CISC 4900 Car Simulation Game Development Log
Week | Date | Logged Event | Duration | Additional Steps
1 | 2022-01-28 | Orientation for CISC 4900 | 1 | Determine Project
1 | 2022-01-29 | Search for project ideas - Develop ideas, search available projects | 2 | Narrow Down project ideas
1 | 2022-01-30 | Search for project ideas | 2
1 | 2022-01-30 | Email prospective supervisors - Drafted & sent 5 emails, received 3 responses, no supervisors acquired | 1
1 | 2022-01-31 | C++ Data Structures Education - C++ basics review (primatives, basic programs) | 3 | Continue C++ education
1 | 2022-01-31 | Respond to emails | 0.25
1 | 2022-01-31 | Email professor to receive supervisor recommendations | 0.25
1 | 2022-02-03 | Respond to email for Supervisor from professor and reach out to supervisor | 0.5 | Get in touch with Supervisor, submit 1st project submission
1 | 2022-02-04 | Meet with supervisor over the phone, make introductions, discuss scope, expectations etc… | 1
1 | 2022-02-05 | C++ Data Structures Education: Arrays - Stacks | 3 | Continue C++ education
|  | Week 1 Total Hours: | 14
2 | 2022-02-07 | C++ Data Structures Education: Queue's & Circular Queues | 4 | Continue C++ education
2 | 2022-02-08 | C++ Data Structures Education: Linked Lists, Strongly Linked Lists, Singly Linked Lists, Doubly Linked Lists | 4 | Continue C++ education
2 | 2022-02-09 | Finish C++ Data Structures Education: Circular Linked Lists, Searching Algorithms | 4.5 | Move on to Unreal Engine Education
2 | 2022-02-11 | Unreal Engine Education: Welcome to Unreal Engine Course | 4.5 | Continue Unreal Engine Education
|  | Week 2 Total Hours: | 17
3 | 2022-02-14 | Unreal Engine Education: Welcome to Unreal Engine Course (finish) | 2.25 | Continue Unreal Engine Education
3 | 2022-02-16 | Unreal Engine Education: UE 5 Early Access Quickstart Course (3 modules) | 3 | Continue Unreal Engine Education
3 | 2022-02-18 | Work on Project Proposal - Start Document | 4
3 | 2022-02-20 | Finalize Project Proposal Document | 6 | Submit proposal document
|  | Week 3 Total Hours: | 15.25
4 | 2022-02-21 | Blender 3D modeling tutorial: Part 1 & 2 | 2.5 | Start with asset creation in Blender (Explore features and gain experience
4 | 2022-02-23 | Set-up Github repository and upload documents | 1
4 | 2022-02-23 | Meet with supervisor over the phone, review Project Proposal and define future meeting schedule. Talk about asset creation | 1
4 | 2022-02-24 | Blender 3D modeling Tesla - Reference Photos search, Car Blueprint search, hood section of car low poly model | 3.5 | Continue with low poly model of Tesla Car - top section
4 | 2022-02-25 | Blender 3D modeling Tesla - top section of vehicle, low poly model | 3 | Continue with low poly model of Tesla Car - rear section
4 | 2022-02-27 | Blender 3D modeling Tesla - Rear portion of vehicle, side of vehicle | 5 | Move on to creation of tires
|  | Week 4 Total Hours: | 16
5 | 2022-02-28 | Blender 3D modeling Tesla- Tires/Wheels | 4 | Move on to headlights, car details
5 | 2022-03-02 | Blender 3D modeling Tesla S model - Headlights, Grille, and Door Handles. | 5 | Add additional vectors for more details, fine tune details
5 | 2022-03-04 | Blender 3D modeling Tesla S - Refining low poly model, adding additional vectors for more precision | 3 | Pause on Tesla model for now, start setup for Hellcat vehicle
5 | 2022-03-06 | Blender 3D modeling Hellcat - Search for Reference Photos, Blueprint, set up References in blender | 3 | Continue with low poly model of Tesla Car
|  | Week 5 Total Hours: | 15
6 | 2022-02-28 | Blender 3D modeling Tesla- Tires/Wheels | 4 | Move on to headlights, car details
6 | 2022-03-02 | Blender 3D modeling Tesla S model - Headlights, Grille, and Door Handles. | 5 | Add additional vectors for more details, fine tune details
6 | 2022-03-04 | Blender 3D modeling Tesla S - Refining low poly model, adding additional vectors for more precision | 3 | Pause on Tesla model for now, start setup for Hellcat vehicle
6 | 2022-03-05 | Blender 3D modeling Hellcat - Search for Reference Photos, Blueprint, set up References in blender | 3 | Continue on Hellcat 3D modeling- start with design of low poly model
6 | 2022-03-06 | Blender 3D modeling Hellcat - Search for Reference Photos, Blueprint, set up References in blender | 3 | Continue on Hellcat 3D modeling- start with design of low poly model
|  | Week 6 Total Hours: | 18
7 | 2022-03-07 | Blender 3D modeling Hellcat - Start on top of vehicle and back of vehicle (low poly model) | 4 | Move on to side of vehicle
7 | 2022-03-09 | Blender 3D modeling Hellcat - side of vehicle completion, rear of side (low poly model) | 3 | Work on Hood, Hood details
7 | 2022-03-11 | Blender 3D modeling Hellcat - Complete hood of vehicle, Hood scoop details | 5 | Pause on Hellcat, Finish Tesla design including fine details
7 | 2022-03-12 | Blender 3D modeling Tesla - Set up color node, lighting, and scene backdrop for test render based on tutorial - This is likely unneccesary for each object in project, but is being completed to gain further knowledge of blender material object nodes | 5 | Upload completed Tesla asset to Github, Render a sample picture and upload to Github repo
|  | Week 7 Total Hours: | 17
8 | 2022-03-15 | Set up meeting with Supervisor for 03/16/2022 | 0.5 | Meet with Supervisor, update on Project status, review render of vehicle
8 | 2022-03-16 | Upload Tesla Asset & Render to GitHub. Upload current Hellcat file to Github repository | 1 | Continue with Hellcat Design
|  | Week 8 Total Hours: | 1.5